## Product backlog
Product Backlog
|  | Organization | LBS, PG19CS15
|  | Project | Online Movie Ticket Booking System
|  | Scrum Master | Harikrishnan V B
|  | Product Owner | Users
Story ID | Category | Title | User story | Value | Sprint #
1 | Security | Login Page | Logging into the website |  | 1
2 | Development | Choose a movie | Choosing movies from the movies offered |  | 2
3 | Development | Booking page | Selecting the location, date, show timing and seats |  | 3
4 | Development | Payment | Enable Payments through debit cards, credit cards, net banking options |  | 4
5 | Development | Profile editing | Changing the name, age, etc. |  | 5
6 | Resolution | Bug fixing | Should be able to book appointments |  | 5

## Sprint 1
Sprint #1Tracking Sheet
|  | Project | Online Movie Ticket Booking System
|  | Sprint # | 1 |  | Start date |  |  | 2022-06-06
|  | Sprint focus | Security
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial Estimate | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15
1 | 1 | Login details: Admin / User | 2
2 | 1 | Login details : Username | 3
3 | 1 | Login details: Password | 3
4 | 1 | Forgot password | 5
5 | 1 | Remember me | 3
|  | Remaining units (actual) | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
|  | Remaining units (ideal) |  | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 16
[12 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project | Online Movie Ticket Booking System
|  | Sprint # | 2 |  | Start date |  |  | 2022-06-16
|  | Sprint focus | Development
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial Estimate | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25
6 | 2 | connecting to database | 5
7 | 2 | search by location | 3
8 | 2 | Searching by movies | 3
9 | 2 | recommended movies | 4
|  | Remaining units (actual) | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
|  | Remaining units (ideal) |  | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 15
[12 empty] | 10 | 0

## Sprint 3
Sprint #3Tracking Sheet
|  | Project | Online Movie Ticket Booking System
|  | Sprint # | 3 |  | Start date |  |  | 2022-06-26
|  | Sprint focus | Development
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial Estimate | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05
10 | 3 | date selection | 3
11 | 3 | theatre selection | 3
12 | 3 | show timing selection | 3
13 | 3 | seat selection | 6
|  | Remaining units (actual) | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
|  | Remaining units (ideal) |  | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 15
[12 empty] | 10 | 0

## Sprint 4
Sprint #4Tracking Sheet
|  | Project | Online Movie Ticket Booking System
|  | Sprint # | 4 |  | Start date |  |  | 2022-07-06
|  | Sprint focus | Development
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial Estimate | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15
14 | 4 | Implementing payment gateway | 12
|  | Remaining units (actual) | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
|  | Remaining units (ideal) |  | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 12
[12 empty] | 10 | 0

## Sprint 5
Sprint #5Tracking Sheet
|  | Project | Online Movie Ticket Booking System
|  | Sprint # | 5 |  | Start date |  |  | 2022-07-16
|  | Sprint focus | Development & Resolution
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial Estimate | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25
15 | 5 | updating the profile picture | 3
16 | 5 | changing the name | 3
17 | 5 | chaning the phone number | 3
18 | 5 | changing the email | 3
19 | 6 | Bug fixing and other refinements | 18
|  | Remaining units (actual) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
|  | Remaining units (ideal) |  | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 30
[12 empty] | 10 | 0